## Summary
Gunvatta Yatra UP – 4-Team Rollout Summary
All figures pull from 'Route Plan' – edit dates/teams there and this sheet updates. Yellow = to fill.
Team | Zone | Team member (1 person) | Home base | Yatras | Districts covered | First solo Yatra | Last Yatra | Joint Yatras attended | Reserve slots
Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) |  |  | 16 | 17 | 2026-10-30 | 2027-03-19 | 1 | 2
Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | Pankaj (confirm) |  | 16 | 17 | 2026-10-30 | 2027-03-19 | 1 | 2
Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj |  |  | 15 | 17 | 2026-10-30 | 2027-03-12 | 1 | 3
Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot |  |  | 15 | 23 | 2026-10-30 | 2027-03-19 | 1 | 3
Joint (All 4) | State launch – all 4 members together | All 4 members |  | 1 | 1 | 2026-10-23 | 2026-10-23 | — | —
TOTAL |  |  |  | 63 | 75 | 2026-10-23 | 2027-03-19 |  | 10
Check: districts covered should equal 75 → |  |  |  |  | ✔ All 75 districts
Yatras per month
Team | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Joint (All 4) | 1 | 0 | 0 | 0 | 0 | 0 | 1
Team 1 – West | 1 | 2 | 2 | 4 | 4 | 3 | 16
Team 2 – East | 1 | 2 | 2 | 4 | 4 | 3 | 16
Team 3 – Central | 1 | 2 | 2 | 4 | 4 | 2 | 15
Team 4 – South-West & Bundelkhand | 1 | 2 | 2 | 4 | 3 | 3 | 15
TOTAL | 5 | 8 | 8 | 16 | 15 | 11 | 63
How the plan works
1. Only the LUCKNOW launch (Fri 23 Oct) is joint – all 4 members together. From Sat 24 Oct each member works independently in his own zone.
2. First solo Yatra on Fri 30 Oct: Bareilly (T1), Gorakhpur (T2), Barabanki (T3), Kanpur Nagar (T4) – all within a day's drive of Lucknow.
3. 6 Nov (Dhanteras/Diwali) and 13 Nov (Bhai Dooj on Wed 11 Nov) are skipped – use these 2 weeks for CMO letters & hospital lists for Circuit 1 and 2.
4. Every Yatra is on FRIDAY; the team member reaches the district Monday/Tuesday (3–4 days for CMO meeting, SPOC, mobilisation).
5. One circuit = 4 neighbouring districts on 4 consecutive Fridays: Circuit 1 (20 Nov–11 Dec), Circuit 2 (Jan), Circuit 3 (Feb), Circuit 4 (Mar) → 4 teams × 4 = 16 Yatras a month.
6. Holiday rule (Friday Calendar sheet): Wed/Thu holiday → week skipped; Friday holiday → Saturday (26 Mar Good Friday → Sat 27 Mar, kept as reserve).
7. All 75 districts finish by 19 Mar 2027. 18 Dec and 27 Mar (plus 26 Feb for T4 and 19 Mar for T3) are RESERVE slots for any postponed Yatra – no April spill-over needed.
8. Up to 4 parallel Yatras every Friday → 4 distinct NABH faculty needed per Friday (Friday Calendar col P).
Formulas:
First solo Yatra = MINIFS('Route Plan'!$J5:J77,'Route Plan'!$C5:C77,[Team],'Route Plan'!$I5:I77,">0")
First solo Yatra = MINIFS('Route Plan'!$J5:J77,'Route Plan'!$C5:C77,[Team])
Last Yatra = MAXIFS('Route Plan'!$J5:J77,'Route Plan'!$C5:C77,[Team],'Route Plan'!$I5:I77,">0")
Last Yatra = MAXIFS('Route Plan'!$J5:J77,'Route Plan'!$C5:C77,[Team])
Zone = COUNTIFS('Route Plan'!$C5:C77,[Team],'Route Plan'!$I5:I77,">0",'Route Plan'!$J5:J77,">="&B14,'Route Plan'!$J5:J77,"<"&EDATE(B14,1))
Team member (1 person) = COUNTIFS('Route Plan'!$C5:C77,[Team],'Route Plan'!$I5:I77,">0",'Route Plan'!$J5:J77,">="&C14,'Route Plan'!$J5:J77,"<"&EDATE(C14,1))
Home base = COUNTIFS('Route Plan'!$C5:C77,[Team],'Route Plan'!$I5:I77,">0",'Route Plan'!$J5:J77,">="&D14,'Route Plan'!$J5:J77,"<"&EDATE(D14,1))
Yatras = COUNTIFS('Route Plan'!$C5:C77,[Team],'Route Plan'!$I5:I77,">0",'Route Plan'!$J5:J77,">="&E14,'Route Plan'!$J5:J77,"<"&EDATE(E14,1))
Districts covered = COUNTIFS('Route Plan'!$C5:C77,[Team],'Route Plan'!$I5:I77,">0",'Route Plan'!$J5:J77,">="&F14,'Route Plan'!$J5:J77,"<"&EDATE(F14,1))

## UP Holidays
UP Holidays & Festivals – Oct 2026 to Apr 2027
Blocks Yatra? = Yes → counts as holiday in the Friday rule · Caution → Yatra allowed but flagged · Edit column E to change the rule. 2027 UP list not yet notified – 2027 dates indicative; Islamic dates moon-dependent.
Date | Day | Holiday / Festival | Type | Blocks Yatra? | Note
2026-10-02 | Friday | Mahatma Gandhi Jayanti | Gazetted | Yes | Before launch
2026-10-19 | Monday | Maha Navami | Gazetted | Yes | Lucknow launch prep week
2026-10-20 | Tuesday | Dussehra / Vijayadashami | Gazetted | Yes | Some lists show 21 Oct (Wed) – if UP notifies 21 Oct, 23 Oct launch falls in a mobilisation-risk week
2026-10-26 | Monday | Maharishi Valmiki Jayanti | Gazetted | Yes | Monday – no clash
2026-10-29 | Thursday | Karva Chauth | Restricted | Caution | Thursday before Gorakhpur (30 Oct)
2026-10-31 | Saturday | Sardar Patel / Acharya Narendra Dev Jayanti | Gazetted | Yes | Saturday
2026-11-06 | Friday | Dhanteras (Diwali week) | Major festival (not gazetted) | Yes | Practical block – hospital owners & CMO staff busy
2026-11-07 | Saturday | Choti Diwali / Narak Chaturdashi | Observance | Yes | Blocks Saturday shift for 6 Nov
2026-11-08 | Sunday | Deepawali | Gazetted | Yes | Sunday
2026-11-09 | Monday | Govardhan Puja | Gazetted | Yes | Some lists show 10 Nov
2026-11-11 | Wednesday | Bhai Dooj / Chitragupta Jayanti | Gazetted | Yes | Wednesday → 13 Nov skipped
2026-11-15 | Sunday | Chhath Puja (evening arghya) | Restricted | Caution | Heavy in East UP – Kushi Nagar moved to 27 Nov
2026-11-16 | Monday | Chhath Puja (morning arghya) | Observance | Caution | East UP staff return mid-week
2026-11-24 | Tuesday | Guru Nanak Jayanti / Kartik Purnima | Gazetted | Yes | Tuesday – no clash
2026-12-23 | Wednesday | Chaudhary Charan Singh Jayanti / Hazrat Ali Jayanti | Gazetted | Yes | Wednesday → 25 Dec week skipped
2026-12-24 | Thursday | Christmas Eve | Restricted | Caution
2026-12-25 | Friday | Christmas | Gazetted | Yes | Friday
2027-01-01 | Friday | New Year's Day | Restricted | Caution | Year-end break applied via override
2027-01-14 | Thursday | Makar Sankranti / Khichdi | Restricted | Caution | Gorakhpur Khichdi mela, Prayagraj Magh Mela, Ayodhya snan – no team in these on 15 Jan
2027-01-26 | Tuesday | Republic Day | National | Yes | Tuesday – no clash
2027-02-11 | Thursday | Basant Panchami (approx.) | Restricted | Caution | Magh Mela snan day – Prayagraj avoided in Feb
2027-02-20 | Saturday | Sant Ravidas Jayanti / Magh Purnima (approx.) | Gazetted | Yes | Saturday
2027-03-06 | Saturday | Maha Shivratri (approx.) | Gazetted | Yes | Saturday
2027-03-09 | Tuesday | Eid-ul-Fitr (approx., moon-dependent) | Gazetted | Yes | If it falls on Wed 10 Mar, 12 Mar Yatras must move to 2 Apr
2027-03-21 | Sunday | Holika Dahan | Gazetted | Yes | Sunday
2027-03-22 | Monday | Holi | Gazetted | Yes | Monday
2027-03-26 | Friday | Good Friday | Gazetted | Yes | Friday → Yatras on Saturday 27 Mar
2027-04-14 | Wednesday | Dr. B.R. Ambedkar Jayanti | Gazetted | Yes | Wednesday → 16 Apr skipped
2027-04-15 | Thursday | Ram Navami (approx.) | Gazetted | Yes

## Route Plan
Gunvatta Yatra UP – 4-Team Route Plan (Friday Yatras)
Ref: SACHIS Circular ABPMJAY/UP-GY/2026-27/161 · Entry Level Certification · Yellow = to fill · Blue km = approx. road distance, verify on maps · Columns Y–Z are helper columns
S.No | Phase / Circuit | Team | Zone | Leg | Mandal | District / Cluster (Host) | Districts covered | No. of districts | Yatra Date | Day | Team on ground by | Travel from | Approx. road km | Calendar check | Earlier GY visit | Venue (Primary) | Fallback | Refreshment & AV | NABH Faculty | District SPOC (CMO office) | Turnout target | Status | Remarks | Week Friday | Key
1 | Joint Launch | Joint (All 4) | State launch – all 4 members together | J-1 | Lucknow | Lucknow | Lucknow | 1 | 2026-10-23 | Friday | 2026-10-19 | Team base |  | YATRA DAY | Yes – 20 attended (11 Hot, 2 Warm). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | GRAND LAUNCH – all 4 members. Prep week overlaps Dussehra (19–20 Oct) – team on ground from Wed 21 Oct. Teams split on Sat 24 Oct | 2026-10-23 | Joint (All 4)¦46318
2 | First solo Yatra (Oct 2026) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C0-L1 | Bareilly | Bareilly | Bareilly | 1 | 2026-10-30 | Friday | 2026-10-26 | Lucknow | 250 | YATRA DAY – CAUTION | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Only ~2 weeks lead time – CMO letter + SPOC needed this week. Karva Chauth Thu 29 Oct | 2026-10-30 | Team 1 – West¦46325
3 | Circuit 1 (Nov–Dec 2026) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C1-L1 | Bareilly | Shahjahanpur | Shahjahanpur | 1 | 2026-11-20 | Friday | 2026-11-16 | Team base |  | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | After Diwali break (31 Oct – 15 Nov) | 2026-11-20 | Team 1 – West¦46346
4 | Circuit 1 (Nov–Dec 2026) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C1-L2 | Bareilly | Pilibhit | Pilibhit | 1 | 2026-11-27 | Friday | 2026-11-23 | Shahjahanpur | 80 | YATRA DAY | Yes – 25 attended (no conversions). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-11-27 | Team 1 – West¦46353
5 | Circuit 1 (Nov–Dec 2026) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C1-L3 | Moradabad | Rampur | Rampur | 1 | 2026-12-04 | Friday | 2026-11-30 | Pilibhit | 110 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-12-04 | Team 1 – West¦46360
6 | Circuit 1 (Nov–Dec 2026) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C1-L4 | Moradabad | Moradabad | Moradabad | 1 | 2026-12-11 | Friday | 2026-12-07 | Rampur | 30 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-12-11 | Team 1 – West¦46367
7 | Reserve | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | R-1 | — | RESERVE SLOT | Buffer for a postponed Yatra | 0 | 2026-12-18 | Friday | 2026-12-14 | — |  | YATRA DAY | — | — | — | — | — | — | — | Reserve | Year-end reserve – use only for a postponed Yatra | 2026-12-18 | Team 1 – West¦46374
8 | Circuit 2 (Jan 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C2-L1 | Saharanpur | Saharanpur | Saharanpur | 1 | 2027-01-08 | Friday | 2027-01-04 | Team base |  | YATRA DAY | Yes – 19 attended (1 Hot, 2 Warm). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-08 | Team 1 – West¦46395
9 | Circuit 2 (Jan 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C2-L2 | Saharanpur | Muzaffarnagar | Muzaffarnagar | 1 | 2027-01-15 | Friday | 2027-01-11 | Saharanpur | 55 | YATRA DAY – CAUTION | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Makar Sankranti Thu 14 Jan (restricted) – early registrations | 2027-01-15 | Team 1 – West¦46402
10 | Circuit 2 (Jan 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C2-L3 | Saharanpur | Shamli | Shamli | 1 | 2027-01-22 | Friday | 2027-01-18 | Muzaffarnagar | 40 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Small district – invite Muzaffarnagar spill-over | 2027-01-22 | Team 1 – West¦46409
11 | Circuit 2 (Jan 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C2-L4 | Meerut | Baghpat | Baghpat | 1 | 2027-01-29 | Friday | 2027-01-25 | Shamli | 75 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-29 | Team 1 – West¦46416
12 | Circuit 3 (Feb 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C3-L1 | Meerut | Meerut | Meerut | 1 | 2027-02-05 | Friday | 2027-02-01 | Team base |  | YATRA DAY | Yes – 30 attended (no conversions). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-05 | Team 1 – West¦46423
13 | Circuit 3 (Feb 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C3-L2 | Meerut | Hapur | Hapur | 1 | 2027-02-12 | Friday | 2027-02-08 | Meerut | 35 | YATRA DAY – CAUTION | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Basant Panchami Thu 11 Feb (restricted) | 2027-02-12 | Team 1 – West¦46430
14 | Circuit 3 (Feb 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C3-L3 | Meerut | Ghaziabad | Ghaziabad | 1 | 2027-02-19 | Friday | 2027-02-15 | Hapur | 35 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-19 | Team 1 – West¦46437
15 | Circuit 3 (Feb 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C3-L4 | Meerut | Gautam Buddha Nagar | Gautam Buddha Nagar | 1 | 2027-02-26 | Friday | 2027-02-22 | Ghaziabad | 35 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-26 | Team 1 – West¦46444
16 | Circuit 4 (Mar 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C4-L1 | Moradabad | Bijnor | Bijnor | 1 | 2027-03-05 | Friday | 2027-03-01 | Team base |  | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-03-05 | Team 1 – West¦46451
17 | Circuit 4 (Mar 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C4-L2 | Moradabad | Amroha | Amroha | 1 | 2027-03-12 | Friday | 2027-03-08 | Bijnor | 70 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Eid-ul-Fitr ~9 Mar (moon) – confirm | 2027-03-12 | Team 1 – West¦46458
18 | Circuit 4 (Mar 2027) | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | C4-L3 | Bareilly | Budaun Cluster | Budaun, Sambhal | 2 | 2027-03-19 | Friday | 2027-03-15 | Amroha | 110 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 80–100 hospitals | Planned | Host: Budaun – invite Sambhal via its CMO | 2027-03-19 | Team 1 – West¦46465
19 | Reserve | Team 1 – West | Bareilly · Moradabad · Saharanpur · Meerut (NCR) | R-2 | — | RESERVE SLOT | Buffer for a postponed Yatra | 0 | 2027-03-27 | Saturday | 2027-03-23 | — |  | SATURDAY (Fri holiday) | — | — | — | — | — | — | — | Reserve | Holi week / Good Friday Saturday – reserve | 2027-03-26 | Team 1 – West¦46472
20 | First solo Yatra (Oct 2026) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C0-L1 | Gorakhpur | Gorakhpur | Gorakhpur | 1 | 2026-10-30 | Friday | 2026-10-26 | Lucknow | 270 | YATRA DAY – CAUTION | Yes – 74 attended (6 Won, 24 Hot). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Already in mobilisation. Karva Chauth Thu 29 Oct | 2026-10-30 | Team 2 – East¦46325
21 | Circuit 1 (Nov–Dec 2026) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C1-L1 | Basti | Basti | Basti | 1 | 2026-11-20 | Friday | 2026-11-16 | Team base |  | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Chhath 15–16 Nov – reach Tue 17 Nov; push registrations by phone before | 2026-11-20 | Team 2 – East¦46346
22 | Circuit 1 (Nov–Dec 2026) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C1-L2 | Basti | Sant Kabir Nagar | Sant Kabir Nagar | 1 | 2026-11-27 | Friday | 2026-11-23 | Basti | 35 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-11-27 | Team 2 – East¦46353
23 | Circuit 1 (Nov–Dec 2026) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C1-L3 | Gorakhpur | Maharajganj | Maharajganj | 1 | 2026-12-04 | Friday | 2026-11-30 | Sant Kabir Nagar | 90 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-12-04 | Team 2 – East¦46360
24 | Circuit 1 (Nov–Dec 2026) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C1-L4 | Gorakhpur | Kushi Nagar | Kushi Nagar | 1 | 2026-12-11 | Friday | 2026-12-07 | Maharajganj | 100 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-12-11 | Team 2 – East¦46367
25 | Reserve | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | R-1 | — | RESERVE SLOT | Buffer for a postponed Yatra | 0 | 2026-12-18 | Friday | 2026-12-14 | — |  | YATRA DAY | — | — | — | — | — | — | — | Reserve | Year-end reserve – use only for a postponed Yatra | 2026-12-18 | Team 2 – East¦46374
26 | Circuit 2 (Jan 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C2-L1 | Basti | Siddharth Nagar | Siddharth Nagar | 1 | 2027-01-08 | Friday | 2027-01-04 | Team base |  | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-08 | Team 2 – East¦46395
27 | Circuit 2 (Jan 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C2-L2 | Devipatan | Balrampur Cluster | Balrampur, Shravasti | 2 | 2027-01-15 | Friday | 2027-01-11 | Siddharth Nagar | 90 | YATRA DAY – CAUTION | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 80–100 hospitals | Planned | Host: Balrampur. Khichdi Thu 14 Jan – Gorakhpur avoided | 2027-01-15 | Team 2 – East¦46402
28 | Circuit 2 (Jan 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C2-L3 | Devipatan | Bahraich | Bahraich | 1 | 2027-01-22 | Friday | 2027-01-18 | Balrampur | 80 | YATRA DAY | Yes – 15 attended (no conversions). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-22 | Team 2 – East¦46409
29 | Circuit 2 (Jan 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C2-L4 | Devipatan | Gonda | Gonda | 1 | 2027-01-29 | Friday | 2027-01-25 | Bahraich | 60 | YATRA DAY | Yes – 21 attended (1 Won). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-29 | Team 2 – East¦46416
30 | Circuit 3 (Feb 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C3-L1 | Gorakhpur | Deoria | Deoria | 1 | 2027-02-05 | Friday | 2027-02-01 | Team base |  | YATRA DAY | Yes – 29 attended (3 Won). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-05 | Team 2 – East¦46423
31 | Circuit 3 (Feb 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C3-L2 | Azamgarh | Ballia | Ballia | 1 | 2027-02-12 | Friday | 2027-02-08 | Deoria | 110 | YATRA DAY – CAUTION | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Basant Panchami Thu 11 Feb (restricted) | 2027-02-12 | Team 2 – East¦46430
32 | Circuit 3 (Feb 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C3-L3 | Azamgarh | Mau | Mau | 1 | 2027-02-19 | Friday | 2027-02-15 | Ballia | 70 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-19 | Team 2 – East¦46437
33 | Circuit 3 (Feb 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C3-L4 | Azamgarh | Azamgarh | Azamgarh | 1 | 2027-02-26 | Friday | 2027-02-22 | Mau | 45 | YATRA DAY | Yes – 11 attended (2 Warm). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-26 | Team 2 – East¦46444
34 | Circuit 4 (Mar 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C4-L1 | Varanasi | Ghazipur | Ghazipur | 1 | 2027-03-05 | Friday | 2027-03-01 | Team base |  | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-03-05 | Team 2 – East¦46451
35 | Circuit 4 (Mar 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C4-L2 | Varanasi | Chandauli | Chandauli | 1 | 2027-03-12 | Friday | 2027-03-08 | Ghazipur | 75 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Eid-ul-Fitr ~9 Mar (moon) – confirm | 2027-03-12 | Team 2 – East¦46458
36 | Circuit 4 (Mar 2027) | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | C4-L3 | Varanasi | Varanasi | Varanasi | 1 | 2027-03-19 | Friday | 2027-03-15 | Chandauli | 30 | YATRA DAY | Yes – 6 attended (2 Hot). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-03-19 | Team 2 – East¦46465
37 | Reserve | Team 2 – East | Gorakhpur · Basti · Devipatan · Azamgarh · Varanasi | R-2 | — | RESERVE SLOT | Buffer for a postponed Yatra | 0 | 2027-03-27 | Saturday | 2027-03-23 | — |  | SATURDAY (Fri holiday) | — | — | — | — | — | — | — | Reserve | Holi week / Good Friday Saturday – reserve | 2027-03-26 | Team 2 – East¦46472
38 | First solo Yatra (Oct 2026) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C0-L1 | Ayodhya | Barabanki | Barabanki | 1 | 2026-10-30 | Friday | 2026-10-26 | Lucknow | 30 | YATRA DAY – CAUTION | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Only ~2 weeks lead time – CMO letter + SPOC needed this week. Karva Chauth Thu 29 Oct | 2026-10-30 | Team 3 – Central¦46325
39 | Circuit 1 (Nov–Dec 2026) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C1-L1 | Lucknow | Sitapur | Sitapur | 1 | 2026-11-20 | Friday | 2026-11-16 | Team base | 90 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | After Diwali break (31 Oct – 15 Nov) | 2026-11-20 | Team 3 – Central¦46346
40 | Circuit 1 (Nov–Dec 2026) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C1-L2 | Lucknow | Lakhimpur Kheri | Lakhimpur Kheri | 1 | 2026-11-27 | Friday | 2026-11-23 | Sitapur | 80 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-11-27 | Team 3 – Central¦46353
41 | Circuit 1 (Nov–Dec 2026) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C1-L3 | Lucknow | Hardoi | Hardoi | 1 | 2026-12-04 | Friday | 2026-11-30 | Lakhimpur Kheri | 130 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-12-04 | Team 3 – Central¦46360
42 | Circuit 1 (Nov–Dec 2026) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C1-L4 | Lucknow | Unnao | Unnao | 1 | 2026-12-11 | Friday | 2026-12-07 | Hardoi | 100 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-12-11 | Team 3 – Central¦46367
43 | Reserve | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | R-1 | — | RESERVE SLOT | Buffer for a postponed Yatra | 0 | 2026-12-18 | Friday | 2026-12-14 | — |  | YATRA DAY | — | — | — | — | — | — | — | Reserve | Year-end reserve – use only for a postponed Yatra | 2026-12-18 | Team 3 – Central¦46374
44 | Circuit 2 (Jan 2027) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C2-L1 | Ayodhya | Amethi | Amethi | 1 | 2027-01-08 | Friday | 2027-01-04 | Team base | 130 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-08 | Team 3 – Central¦46395
45 | Circuit 2 (Jan 2027) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C2-L2 | Ayodhya | Sultanpur | Sultanpur | 1 | 2027-01-15 | Friday | 2027-01-11 | Amethi | 40 | YATRA DAY – CAUTION | Yes – 35 attended (1 Won, 6 Warm). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Makar Sankranti Thu 14 Jan – Ayodhya kept to 29 Jan | 2027-01-15 | Team 3 – Central¦46402
46 | Circuit 2 (Jan 2027) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C2-L3 | Ayodhya | Ambedkar Nagar | Ambedkar Nagar | 1 | 2027-01-22 | Friday | 2027-01-18 | Sultanpur | 70 | YATRA DAY | Yes – 32 attended (4 Won). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-22 | Team 3 – Central¦46409
47 | Circuit 2 (Jan 2027) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C2-L4 | Ayodhya | Ayodhya | Ayodhya | 1 | 2027-01-29 | Friday | 2027-01-25 | Ambedkar Nagar | 60 | YATRA DAY | Yes – 32 attended (2 Won). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-29 | Team 3 – Central¦46416
48 | Circuit 3 (Feb 2027) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C3-L1 | Varanasi | Jaunpur | Jaunpur | 1 | 2027-02-05 | Friday | 2027-02-01 | Team base |  | YATRA DAY | Yes – 22 attended (2 Won, 3 Hot). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-05 | Team 3 – Central¦46423
49 | Circuit 3 (Feb 2027) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C3-L2 | Vindhyachal | Bhadohi | Bhadohi | 1 | 2027-02-12 | Friday | 2027-02-08 | Jaunpur | 60 | YATRA DAY – CAUTION | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Basant Panchami Thu 11 Feb (restricted) | 2027-02-12 | Team 3 – Central¦46430
50 | Circuit 3 (Feb 2027) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C3-L3 | Vindhyachal | Mirzapur | Mirzapur | 1 | 2027-02-19 | Friday | 2027-02-15 | Bhadohi | 45 | YATRA DAY | Yes – 27 attended (no conversions). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-19 | Team 3 – Central¦46437
51 | Circuit 3 (Feb 2027) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C3-L4 | Vindhyachal | Sonbhadra | Sonbhadra | 1 | 2027-02-26 | Friday | 2027-02-22 | Mirzapur | 90 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-26 | Team 3 – Central¦46444
52 | Circuit 4 (Mar 2027) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C4-L1 | Prayagraj | Pratapgarh Cluster | Pratapgarh, Rae Bareli, Kaushambi | 3 | 2027-03-05 | Friday | 2027-03-01 | Team base |  | YATRA DAY | Yes – 20 attended (Pratapgarh only). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 80–100 hospitals | Planned | Host: Pratapgarh – after Magh Mela | 2027-03-05 | Team 3 – Central¦46451
53 | Circuit 4 (Mar 2027) | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | C4-L2 | Prayagraj | Prayagraj | Prayagraj | 1 | 2027-03-12 | Friday | 2027-03-08 | Pratapgarh | 60 | YATRA DAY | Yes – 30 attended (8 in progress, 7 Hot). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Eid-ul-Fitr ~9 Mar (moon) – confirm | 2027-03-12 | Team 3 – Central¦46458
54 | Reserve | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | R-2 | — | RESERVE SLOT | Buffer for a postponed Yatra | 0 | 2027-03-19 | Friday | 2027-03-15 | — |  | YATRA DAY | — | — | — | — | — | — | — | Reserve | Reserve – Team 3 finishes early | 2027-03-19 | Team 3 – Central¦46465
55 | Reserve | Team 3 – Central | Lucknow belt · Ayodhya · Jaunpur–Vindhyachal · Prayagraj | R-3 | — | RESERVE SLOT | Buffer for a postponed Yatra | 0 | 2027-03-27 | Saturday | 2027-03-23 | — |  | SATURDAY (Fri holiday) | — | — | — | — | — | — | — | Reserve | Holi week / Good Friday Saturday – reserve | 2027-03-26 | Team 3 – Central¦46472
56 | First solo Yatra (Oct 2026) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C0-L1 | Kanpur | Kanpur Nagar | Kanpur Nagar | 1 | 2026-10-30 | Friday | 2026-10-26 | Lucknow | 90 | YATRA DAY – CAUTION | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Only ~2 weeks lead time – CMO letter + SPOC needed this week. Large hospital base – 60+ seats | 2026-10-30 | Team 4 – South-West & Bundelkhand¦46325
57 | Circuit 1 (Nov–Dec 2026) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C1-L1 | Prayagraj | Fatehpur | Fatehpur | 1 | 2026-11-20 | Friday | 2026-11-16 | Team base |  | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | After Diwali break (31 Oct – 15 Nov) | 2026-11-20 | Team 4 – South-West & Bundelkhand¦46346
58 | Circuit 1 (Nov–Dec 2026) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C1-L2 | Kanpur | Kanpur Dehat | Kanpur Dehat | 1 | 2026-11-27 | Friday | 2026-11-23 | Fatehpur | 120 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-11-27 | Team 4 – South-West & Bundelkhand¦46353
59 | Circuit 1 (Nov–Dec 2026) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C1-L3 | Kanpur | Etawah | Etawah | 1 | 2026-12-04 | Friday | 2026-11-30 | Kanpur Dehat | 110 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2026-12-04 | Team 4 – South-West & Bundelkhand¦46360
60 | Circuit 1 (Nov–Dec 2026) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C1-L4 | Kanpur | Farrukhabad Cluster | Farrukhabad, Kannauj, Auraiya | 3 | 2026-12-11 | Friday | 2026-12-07 | Etawah | 120 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 80–100 hospitals | Planned | Host: Farrukhabad | 2026-12-11 | Team 4 – South-West & Bundelkhand¦46367
61 | Reserve | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | R-1 | — | RESERVE SLOT | Buffer for a postponed Yatra | 0 | 2026-12-18 | Friday | 2026-12-14 | — |  | YATRA DAY | — | — | — | — | — | — | — | Reserve | Year-end reserve – use only for a postponed Yatra | 2026-12-18 | Team 4 – South-West & Bundelkhand¦46374
62 | Circuit 2 (Jan 2027) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C2-L1 | Agra | Mainpuri | Mainpuri | 1 | 2027-01-08 | Friday | 2027-01-04 | Team base |  | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-08 | Team 4 – South-West & Bundelkhand¦46395
63 | Circuit 2 (Jan 2027) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C2-L2 | Agra | Firozabad | Firozabad | 1 | 2027-01-15 | Friday | 2027-01-11 | Mainpuri | 55 | YATRA DAY – CAUTION | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned | Makar Sankranti Thu 14 Jan (restricted) | 2027-01-15 | Team 4 – South-West & Bundelkhand¦46402
64 | Circuit 2 (Jan 2027) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C2-L3 | Agra | Agra | Agra | 1 | 2027-01-22 | Friday | 2027-01-18 | Firozabad | 45 | YATRA DAY | Yes – 14 attended (3 Won). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-22 | Team 4 – South-West & Bundelkhand¦46409
65 | Circuit 2 (Jan 2027) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C2-L4 | Agra | Mathura | Mathura | 1 | 2027-01-29 | Friday | 2027-01-25 | Agra | 60 | YATRA DAY | Yes – 42 attended (no conversions). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-01-29 | Team 4 – South-West & Bundelkhand¦46416
66 | Circuit 3 (Feb 2027) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C3-L1 | Aligarh | Aligarh | Aligarh | 1 | 2027-02-05 | Friday | 2027-02-01 | Team base |  | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-05 | Team 4 – South-West & Bundelkhand¦46423
67 | Circuit 3 (Feb 2027) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C3-L2 | Aligarh | Hathras Cluster | Hathras, Etah, Kasganj | 3 | 2027-02-12 | Friday | 2027-02-08 | Aligarh | 40 | YATRA DAY – CAUTION | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 80–100 hospitals | Planned | Host: Hathras. Basant Panchami Thu 11 Feb (restricted) | 2027-02-12 | Team 4 – South-West & Bundelkhand¦46430
68 | Circuit 3 (Feb 2027) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C3-L3 | Meerut | Bulandshahar | Bulandshahar | 1 | 2027-02-19 | Friday | 2027-02-15 | Hathras | 110 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-02-19 | Team 4 – South-West & Bundelkhand¦46437
69 | Reserve | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | R-2 | — | RESERVE SLOT | Buffer for a postponed Yatra | 0 | 2027-02-26 | Friday | 2027-02-22 | — |  | YATRA DAY | — | — | — | — | — | — | — | Reserve | Reserve | 2027-02-26 | Team 4 – South-West & Bundelkhand¦46444
70 | Circuit 4 (Mar 2027) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C4-L1 | Jhansi | Jhansi | Jhansi | 1 | 2027-03-05 | Friday | 2027-03-01 | Team base |  | YATRA DAY | Yes – 41 attended (8 in progress, 14 Hot). Run as follow-up | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 40–50 hospitals | Planned |  | 2027-03-05 | Team 4 – South-West & Bundelkhand¦46451
71 | Circuit 4 (Mar 2027) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C4-L2 | Jhansi | Orai (Jalaun) Cluster | Jalaun, Lalitpur | 2 | 2027-03-12 | Friday | 2027-03-08 | Jhansi | 120 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 80–100 hospitals | Planned | Host: Orai. Eid-ul-Fitr ~9 Mar (moon) – confirm | 2027-03-12 | Team 4 – South-West & Bundelkhand¦46458
72 | Circuit 4 (Mar 2027) | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | C4-L3 | Chitrakoot | Banda Cluster | Banda, Chitrakoot, Mahoba, Hamirpur | 4 | 2027-03-19 | Friday | 2027-03-15 | Orai | 150 | YATRA DAY | New district | CMO Office | QCI Procurement | CMO / QCI – to be locked |  |  | 80–100 hospitals | Planned | Host: Banda – before Holi week | 2027-03-19 | Team 4 – South-West & Bundelkhand¦46465
73 | Reserve | Team 4 – South-West & Bundelkhand | Kanpur · Agra · Aligarh · Jhansi · Chitrakoot | R-3 | — | RESERVE SLOT | Buffer for a postponed Yatra | 0 | 2027-03-27 | Saturday | 2027-03-23 | — |  | SATURDAY (Fri holiday) | — | — | — | — | — | — | — | Reserve | Holi week / Good Friday Saturday – reserve | 2027-03-26 | Team 4 – South-West & Bundelkhand¦46472
[6 empty] | TOTAL | Districts (col I) · Yatras (col J) | 75 | 73
Formulas:
Team on ground by = [Yatra Date]-4
Week Friday = [Yatra Date]-IF(WEEKDAY([Yatra Date],2)=6,1,0)
Note on N4: Approximate road distance between district HQs, from the previous stop in the same team's route. Blank = travel from team base / home after a break. Verify on Google Maps.

## Friday Calendar
Friday Calendar – Holiday & Mobilisation Check
Rule: Wed/Thu holiday → SKIP (participant mobilisation) · Friday holiday → SATURDAY · Caution = Yatra allowed, push registrations early · Override (yellow) beats the rule
Friday | Team on ground (Mon) | Wed holiday | Thu holiday | Fri holiday | Sat holiday | Wed/Thu blocks | Fri blocks | Sat blocks | Caution count | Rule result | Planning override | FINAL STATUS | Yatra date to use | Yatras scheduled | NABH faculty needed
2026-10-23 | 2026-10-19 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2026-10-23 | 1 | 1
2026-10-30 | 2026-10-26 |  | Karva Chauth |  | Sardar Patel / Acharya Narendra Dev Jayanti | 0 | 0 | 1 | 1 | YATRA DAY – CAUTION |  | YATRA DAY – CAUTION | 2026-10-30 | 4 | 4
2026-11-06 | 2026-11-02 |  |  | Dhanteras (Diwali week) | Choti Diwali / Narak Chaturdashi | 0 | 1 | 1 | 0 | SKIP – Fri & Sat holiday |  | SKIP – Fri & Sat holiday |  | 0 | 0
2026-11-13 | 2026-11-09 | Bhai Dooj / Chitragupta Jayanti |  |  |  | 1 | 0 | 0 | 0 | SKIP – Wed/Thu holiday |  | SKIP – Wed/Thu holiday |  | 0 | 0
2026-11-20 | 2026-11-16 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2026-11-20 | 4 | 4
2026-11-27 | 2026-11-23 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2026-11-27 | 4 | 4
2026-12-04 | 2026-11-30 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2026-12-04 | 4 | 4
2026-12-11 | 2026-12-07 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2026-12-11 | 4 | 4
2026-12-18 | 2026-12-14 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2026-12-18 | 0 | 0
2026-12-25 | 2026-12-21 | Chaudhary Charan Singh Jayanti / Hazrat Ali Jayanti | Christmas Eve | Christmas |  | 1 | 1 | 0 | 1 | SKIP – Wed/Thu holiday |  | SKIP – Wed/Thu holiday |  | 0 | 0
2027-01-01 | 2026-12-28 |  |  | New Year's Day |  | 0 | 0 | 0 | 1 | YATRA DAY – CAUTION | SKIP – year-end break (19 Dec–3 Jan) | SKIP – year-end break (19 Dec–3 Jan) |  | 0 | 0
2027-01-08 | 2027-01-04 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2027-01-08 | 4 | 4
2027-01-15 | 2027-01-11 |  | Makar Sankranti / Khichdi |  |  | 0 | 0 | 0 | 1 | YATRA DAY – CAUTION |  | YATRA DAY – CAUTION | 2027-01-15 | 4 | 4
2027-01-22 | 2027-01-18 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2027-01-22 | 4 | 4
2027-01-29 | 2027-01-25 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2027-01-29 | 4 | 4
2027-02-05 | 2027-02-01 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2027-02-05 | 4 | 4
2027-02-12 | 2027-02-08 |  | Basant Panchami (approx.) |  |  | 0 | 0 | 0 | 1 | YATRA DAY – CAUTION |  | YATRA DAY – CAUTION | 2027-02-12 | 4 | 4
2027-02-19 | 2027-02-15 |  |  |  | Sant Ravidas Jayanti / Magh Purnima (approx.) | 0 | 0 | 1 | 0 | YATRA DAY |  | YATRA DAY | 2027-02-19 | 4 | 4
2027-02-26 | 2027-02-22 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2027-02-26 | 3 | 3
2027-03-05 | 2027-03-01 |  |  |  | Maha Shivratri (approx.) | 0 | 0 | 1 | 0 | YATRA DAY |  | YATRA DAY | 2027-03-05 | 4 | 4
2027-03-12 | 2027-03-08 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2027-03-12 | 4 | 4
2027-03-19 | 2027-03-15 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2027-03-19 | 3 | 3
2027-03-26 | 2027-03-22 |  |  | Good Friday |  | 0 | 1 | 0 | 0 | SATURDAY (Fri holiday) |  | SATURDAY (Fri holiday) | 2027-03-27 | 0 | 0
2027-04-02 | 2027-03-29 |  |  |  |  | 0 | 0 | 0 | 0 | YATRA DAY |  | YATRA DAY | 2027-04-02 | 0 | 0
TOTAL | [13 empty] | 63 | 63
Formulas:
Team on ground (Mon) = [Friday]-4
Yatra date to use = IF(LEFT([FINAL STATUS],4)="SKIP","",IF(LEFT([FINAL STATUS],8)="SATURDAY",[Friday]+1,[Friday]))

## Route Matrix
Route Matrix – Week-by-Week, Team-by-Team
Each column is one person's route. Only Lucknow (23 Oct) is joint. One circuit = 4 consecutive Fridays in neighbouring districts.
Week (Friday) | Yatra date | Calendar status | Joint (All 4) | Team 1 – West | Team 2 – East | Team 3 – Central | Team 4 – South-West & Bundelkhand | Yatras this week | NABH faculty needed
2026-10-23 | 2026-10-23 | YATRA DAY | Lucknow |  |  |  |  | 1 | 1
2026-10-30 | 2026-10-30 | YATRA DAY – CAUTION |  | Bareilly | Gorakhpur | Barabanki | Kanpur Nagar | 4 | 4
2026-11-06 | — | SKIP – Fri & Sat holiday | [5 empty] | 0 | 0
2026-11-13 | — | SKIP – Wed/Thu holiday | [5 empty] | 0 | 0
2026-11-20 | 2026-11-20 | YATRA DAY |  | Shahjahanpur | Basti | Sitapur | Fatehpur | 4 | 4
2026-11-27 | 2026-11-27 | YATRA DAY |  | Pilibhit | Sant Kabir Nagar | Lakhimpur Kheri | Kanpur Dehat | 4 | 4
2026-12-04 | 2026-12-04 | YATRA DAY |  | Rampur | Maharajganj | Hardoi | Etawah | 4 | 4
2026-12-11 | 2026-12-11 | YATRA DAY |  | Moradabad | Kushi Nagar | Unnao | Farrukhabad Cluster | 4 | 4
2026-12-18 | 2026-12-18 | YATRA DAY |  | RESERVE SLOT | RESERVE SLOT | RESERVE SLOT | RESERVE SLOT | 0 | 0
2026-12-25 | — | SKIP – Wed/Thu holiday | [5 empty] | 0 | 0
2027-01-01 | — | SKIP – year-end break (19 Dec–3 Jan) | [5 empty] | 0 | 0
2027-01-08 | 2027-01-08 | YATRA DAY |  | Saharanpur | Siddharth Nagar | Amethi | Mainpuri | 4 | 4
2027-01-15 | 2027-01-15 | YATRA DAY – CAUTION |  | Muzaffarnagar | Balrampur Cluster | Sultanpur | Firozabad | 4 | 4
2027-01-22 | 2027-01-22 | YATRA DAY |  | Shamli | Bahraich | Ambedkar Nagar | Agra | 4 | 4
2027-01-29 | 2027-01-29 | YATRA DAY |  | Baghpat | Gonda | Ayodhya | Mathura | 4 | 4
2027-02-05 | 2027-02-05 | YATRA DAY |  | Meerut | Deoria | Jaunpur | Aligarh | 4 | 4
2027-02-12 | 2027-02-12 | YATRA DAY – CAUTION |  | Hapur | Ballia | Bhadohi | Hathras Cluster | 4 | 4
2027-02-19 | 2027-02-19 | YATRA DAY |  | Ghaziabad | Mau | Mirzapur | Bulandshahar | 4 | 4
2027-02-26 | 2027-02-26 | YATRA DAY |  | Gautam Buddha Nagar | Azamgarh | Sonbhadra | RESERVE SLOT | 3 | 3
2027-03-05 | 2027-03-05 | YATRA DAY |  | Bijnor | Ghazipur | Pratapgarh Cluster | Jhansi | 4 | 4
2027-03-12 | 2027-03-12 | YATRA DAY |  | Amroha | Chandauli | Prayagraj | Orai (Jalaun) Cluster | 4 | 4
2027-03-19 | 2027-03-19 | YATRA DAY |  | Budaun Cluster | Varanasi | RESERVE SLOT | Banda Cluster | 3 | 3
2027-03-26 | 2027-03-27 | SATURDAY (Fri holiday) |  | RESERVE SLOT | RESERVE SLOT | RESERVE SLOT | RESERVE SLOT | 0 | 0
2027-04-02 | 2027-04-02 | YATRA DAY | [5 empty] | 0 | 0
TOTAL |  |  | 1 | 16 | 16 | 15 | 15 | 63 | 63

## Weekly Rhythm
Weekly Rhythm – One Yatra Week (per team member)
Same rhythm every week; for a Saturday Yatra shift every row by one day
When | Activity | Output / check | With
T-30 (month before circuit) | Send QCI letter (citing SACHIS Circular 161) to all 4 CMOs of the next circuit; request hospital list + SPOC | Letters dispatched for all 4 districts | CMO offices
T-15 | Pre-build target list: PM-JAY empanelled hospitals minus NABH-certified; ask CMO only to validate | District target list ready | Analyst / CMO
T-10 | Venue confirmed by CMO – else trigger QCI Procurement; decide Refreshment & AV owner | Venue + AV locked | CMO / QCI Procurement
T-7 | Confirm NABH faculty for the date (distinct faculty for each parallel Yatra) | Faculty confirmed | NABH coordinator
Monday | Reach district; meet CMO / Dy. CMO; confirm SPOC; collect & validate hospital list | SPOC named, list validated | CMO office
Tuesday | CMO invitation circulated; CRM registration link shared; calls to top 60 non-NABH hospitals | Registrations started | SPOC
Wednesday | Visit key hospitals / IMA branch; venue walk-through; refreshment & AV order confirmed | ≥25 registrations | SPOC / vendor
Thursday | Reminder calls & WhatsApp; print material, standees, feedback forms; faculty travel check | ≥40 registrations; faculty en route | SPOC / faculty
Friday 4–8 PM | YATRA – Registration, QCI intro, NABH technical session, Q&A, Pledge, Vote of thanks, Group photo | Attendance + feedback captured | NABH faculty
Saturday | Update CRM: Hot / Warm / Cold; send thank-you + next steps; travel to next district | CRM updated within 24 hrs | Team member
Sunday | Rest / travel | — | —

## Notes & Risks
Assumptions, Open Items & Risks
# | Item | Detail / Action | Level
1 | 30 Oct lead time | Bareilly, Barabanki and Kanpur Nagar get only ~2 weeks (Gorakhpur is already being mobilised). Send CMO letters + get SPOCs this week; if a CMO cannot confirm by 20 Oct, move that district to its 18 Dec reserve and run its Circuit 1 district instead. | High
2 | Holiday data | 2026 dates from published UP holiday lists; 2027 UP list not yet notified – 2027 dates indicative. Update 'UP Holidays' once GAD notifies (usually Dec); the calendar re-checks automatically. | Medium
3 | Dussehra date | Lists differ (20 Oct Tue vs 21 Oct Wed). If 21 Oct is notified, the Lucknow launch week is a Wed-holiday week – mobilise before Dussehra. | High
4 | Chhath | Team 2's Basti (20 Nov) comes right after Chhath (15–16 Nov) – reach Tue 17 Nov and finish phone mobilisation before the festival. | Medium
5 | Eid-ul-Fitr | Expected ~9 Mar 2027 (Tue). If moon puts it on Wed 10 Mar, the 12 Mar Yatras move to the 27 Mar / 19 Mar reserve slots. | Medium
6 | UP Assembly election 2027 | Likely Feb–Mar 2027. Once Model Code of Conduct applies, CMO/DM staff go on poll duty and govt halls get requisitioned – book QCI-procured venues for Feb–Mar, no political guests, avoid each district's poll date ±3 days. | High
7 | Fog / timing | Dec–Feb dense fog: an 8 PM finish means night highway driving. Consider 2–6 PM sessions Dec–Feb, or overnight stay. | Medium
8 | Clusters | 7 cluster Yatras (host + neighbours). Ask CMOs of ALL cluster districts to mobilise, not only the host; consider 12–4 PM so hospitals can travel back. | Medium
9 | Single-person teams | No backup if a member falls sick. Use reserve slots; name one standby person who can step into any zone. | Medium
10 | NABH faculty | 4 parallel Yatras every Friday from 30 Oct → pool of 5–6 faculty, block dates month-wise, confirm at T-7. | High
11 | Distances | Road km are approximate HQ-to-HQ figures for route planning only – verify before booking travel. | Low
12 | Gunvatta Manthan | Earlier reserve date 31 Mar 2027 = financial-year close + possible new govt. Suggest mid-April 2027. | Medium