## All Yatras
Phase | Yatra # | Event Date | Day | Time | Rath / Mode | Cluster | Role | Mandal | District | Zone | Tier | Visit Type | PM-JAY Universe | NABH Total | Certified | Accredited | Potential Gap | % Potential | Yatras Conducted | Attended | Won | Application in Progress | Hot | Warm
TOTAL | 63 yatras | [7 empty] | 75 districts |  |  |  | 3650 | 1404 | 955 | 449 | 2246 | 61.53% | 25 | 509 | 22 | 22 | 71 | 25
Phase 1 | 1 | 2026-10-09 | Friday | 4 PM - 8 PM | Launch (Rath A + B) |  | Host | Gorakhpur | Gorakhpur | Eastern UP | Tier 3 | Follow-up | 211 | 68 | 58 | 10 | 143 | 67.77% | 3 | 74 | 6 | 1 | 24 | 3
Phase 1 | 2 | 2026-10-14 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Bareilly | Bareilly | Western UP | Tier 3 | New | 211 | 90 | 57 | 33 | 121 | 57.35%
Phase 1 | 3 | 2026-10-14 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Gorakhpur | Kushi Nagar | Eastern UP | Tier 3 | New | 47 | 3 | 3 | 0 | 44 | 93.62%
Phase 1 | 4 | 2026-10-16 | Friday | 4 PM - 8 PM | Rath A |  | Host | Moradabad | Moradabad | Western UP | Tier 3 | New | 103 | 40 | 26 | 14 | 63 | 61.17%
Phase 1 | 5 | 2026-10-16 | Friday | 4 PM - 8 PM | Rath B |  | Host | Gorakhpur | Maharajganj | Eastern UP | Tier 3 | New | 24 | 1 | 1 | 0 | 23 | 95.83%
Phase 1 | 6 | 2026-10-23 | Friday | 4 PM - 8 PM | Rath A |  | Host | Moradabad | Bijnor | Western UP | Tier 3 | New | 91 | 21 | 21 | 0 | 70 | 76.92%
Phase 1 | 7 | 2026-10-23 | Friday | 4 PM - 8 PM | Rath B |  | Host | Basti | Sant Kabir Nagar | Eastern UP | Tier 3 | New | 46 | 7 | 7 | 0 | 39 | 84.78%
Phase 1 | 8 | 2026-10-28 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Saharanpur | Muzaffarnagar | Western UP | Tier 3 | New | 44 | 21 | 19 | 2 | 23 | 52.27%
Phase 1 | 9 | 2026-10-28 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Basti | Basti | Eastern UP | Tier 3 | New | 78 | 11 | 10 | 1 | 67 | 85.9%
Phase 1 | 10 | 2026-10-30 | Friday | 4 PM - 8 PM | Rath A |  | Host | Saharanpur | Saharanpur | Western UP | Tier 3 | Follow-up | 80 | 34 | 32 | 2 | 46 | 57.5% | 2 | 19 | 0 | 0 | 1 | 2
Phase 1 | 11 | 2026-10-30 | Friday | 4 PM - 8 PM | Rath B |  | Host | Ayodhya | Barabanki | Eastern UP | Tier 3 | New | 42 | 4 | 3 | 1 | 38 | 90.48%
Phase 1 | 12 | 2026-11-04 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Saharanpur | Shamli | Western UP | Tier 3 | New | 39 | 9 | 8 | 1 | 30 | 76.92%
Phase 1 | 13 | 2026-11-04 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Lucknow | Lakhimpur Kheri | Central UP | Tier 3 | New | 21 | 1 | 1 | 0 | 20 | 95.24%
Phase 1 | 14 | 2026-11-13 | Friday | 4 PM - 8 PM | Rath A |  | Host | Meerut | Bulandshahar | Western UP | Tier 3 | New | 100 | 49 | 41 | 8 | 51 | 51%
Phase 1 | 15 | 2026-11-13 | Friday | 4 PM - 8 PM | Rath B |  | Host | Prayagraj | Prayagraj | Eastern UP | Tier 3 | Follow-up | 179 | 45 | 23 | 22 | 134 | 74.86% | 1 | 30 | 0 | 8 | 7 | 0
Phase 1 | 16 | 2026-11-18 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Meerut | Hapur | Western UP | Tier 3 | New | 37 | 6 | 5 | 1 | 31 | 83.78%
Phase 1 | 17 | 2026-11-18 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Vindhyachal | Mirzapur | Eastern UP | Tier 3 | Follow-up | 33 | 8 | 5 | 3 | 25 | 75.76% | 1 | 27 | 0 | 0 | 0 | 0
Phase 1 | 18 | 2026-11-20 | Friday | 4 PM - 8 PM | Rath A |  | Host | Aligarh | Aligarh | Western UP | Tier 3 | New | 70 | 29 | 24 | 5 | 41 | 58.57%
Phase 1 | 19 | 2026-11-20 | Friday | 4 PM - 8 PM | Rath B |  | Host | Vindhyachal | Bhadohi | Eastern UP | Tier 3 | New | 35 | 4 | 4 | 0 | 31 | 88.57%
Phase 1 | 20 | 2026-11-25 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Kanpur | Kanpur Nagar | Central UP | Tier 2 | New | 194 | 90 | 60 | 30 | 104 | 53.61%
Phase 1 | 21 | 2026-11-25 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Varanasi | Chandauli | Eastern UP | Tier 3 | New | 62 | 9 | 9 | 0 | 53 | 85.48%
Phase 1 | 22 | 2026-11-27 | Friday | 4 PM - 8 PM | Rath A |  | Host | Jhansi | Jhansi | Bundelkhand (South UP) | Tier 3 | Follow-up | 71 | 34 | 31 | 3 | 37 | 52.11% | 1 | 41 | 0 | 8 | 14 | 0
Phase 1 | 23 | 2026-11-27 | Friday | 4 PM - 8 PM | Rath B |  | Host | Azamgarh | Mau | Eastern UP | Tier 3 | New | 36 | 4 | 2 | 2 | 32 | 88.89%
Phase 2 | 1 | 2027-01-06 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Varanasi | Jaunpur | Eastern UP | Tier 3 | Follow-up | 58 | 9 | 9 | 0 | 49 | 84.48% | 1 | 22 | 2 | 1 | 3 | 2
Phase 2 | 2 | 2027-01-06 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Meerut | Meerut | Western UP | Tier 3 | Follow-up | 129 | 67 | 40 | 27 | 62 | 48.06% | 1 | 30 | 0 | 0 | 0 | 0
Phase 2 | 3 | 2027-01-08 | Friday | 4 PM - 8 PM | Rath A |  | Host | Gorakhpur | Deoria | Eastern UP | Tier 3 | Follow-up | 32 | 5 | 5 | 0 | 27 | 84.38% | 1 | 29 | 3 | 0 | 3 | 1
Phase 2 | 4 | 2027-01-08 | Friday | 4 PM - 8 PM | Rath B |  | Host | Agra | Agra | Western UP | Tier 2 | Follow-up | 89 | 56 | 45 | 11 | 33 | 37.08% | 2 | 14 | 3 | 0 | 2 | 3
Phase 2 | 5 | 2027-01-13 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Ayodhya | Ambedkar Nagar | Eastern UP | Tier 3 | Follow-up | 30 | 3 | 3 | 0 | 27 | 90% | 1 | 32 | 4 | 2 | 1 | 3
Phase 2 | 6 | 2027-01-13 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Agra | Mathura | Western UP | Tier 3 | Follow-up | 70 | 25 | 21 | 4 | 45 | 64.29% | 2 | 42 | 0 | 0 | 0 | 0
Phase 2 | 7 | 2027-01-15 | Friday | 4 PM - 8 PM | Rath A |  | Host | Ayodhya | Ayodhya | Eastern UP | Tier 3 | Follow-up | 30 | 7 | 6 | 1 | 23 | 76.67% | 1 | 32 | 2 | 1 | 2 | 1
Phase 2 | 8 | 2027-01-15 | Friday | 4 PM - 8 PM | Rath B |  | Host | Bareilly | Pilibhit | Western UP | Tier 3 | Follow-up | 27 | 4 | 3 | 1 | 23 | 85.19% | 1 | 25 | 0 | 0 | 0 | 0
Phase 2 | 9 | 2027-01-20 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Ayodhya | Sultanpur | Eastern UP | Tier 3 | Follow-up | 37 | 7 | 7 | 0 | 30 | 81.08% | 1 | 35 | 1 | 1 | 1 | 6
Phase 2 | 10 | 2027-01-20 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Bareilly | Shahjahanpur | Western UP | Tier 3 | New | 32 | 11 | 10 | 1 | 21 | 65.62%
Phase 2 | 11 | 2027-01-22 | Friday | 4 PM - 8 PM | Rath A |  | Host | Ayodhya | Amethi | Eastern UP | Tier 3 | New | 24 | 3 | 3 | 0 | 21 | 87.5%
Phase 2 | 12 | 2027-01-22 | Friday | 4 PM - 8 PM | Rath B |  | Host | Moradabad | Rampur | Western UP | Tier 3 | New | 23 | 5 | 4 | 1 | 18 | 78.26%
Phase 2 | 13 | 2027-01-27 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Devipatan | Gonda | Eastern UP | Tier 3 | Follow-up | 29 | 4 | 4 | 0 | 25 | 86.21% | 1 | 0 | 1 | 0 | 0 | 0
Phase 2 | 14 | 2027-01-27 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Moradabad | Amroha | Western UP | Tier 3 | New | 23 | 7 | 4 | 3 | 16 | 69.57%
Phase 2 | 15 | 2027-01-29 | Friday | 4 PM - 8 PM | Rath A |  | Host | Varanasi | Varanasi | Eastern UP | Tier 3 | Follow-up | 231 | 90 | 57 | 33 | 141 | 61.04% | 1 | 6 | 0 | 0 | 2 | 0
Phase 2 | 16 | 2027-01-29 | Friday | 4 PM - 8 PM | Rath B |  | Host | Meerut | Baghpat | Western UP | Tier 3 | New | 24 | 8 | 7 | 1 | 16 | 66.67%
Phase 2 | 17 | 2027-02-03 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Lucknow | Lucknow | Central UP | Tier 2 | Follow-up | 326 | 137 | 90 | 47 | 189 | 57.98% | 1 | 20 | 0 | 0 | 11 | 2
Phase 2 | 18 | 2027-02-03 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Lucknow | Hardoi | Central UP | Tier 3 | New | 19 | 1 | 1 | 0 | 18 | 94.74%
Phase 2 | 19 | 2027-02-05 | Friday | 4 PM - 8 PM | Rath A |  | Host | Azamgarh | Azamgarh | Eastern UP | Tier 3 | Follow-up | 36 | 16 | 14 | 2 | 20 | 55.56% | 1 | 11 | 0 | 0 | 0 | 2
Phase 2 | 20 | 2027-02-05 | Friday | 4 PM - 8 PM | Rath B |  | Host | Lucknow | Sitapur | Central UP | Tier 3 | New | 19 | 3 | 2 | 1 | 16 | 84.21%
Phase 2 | 21 | 2027-02-10 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Varanasi | Ghazipur | Eastern UP | Tier 3 | New | 20 | 4 | 3 | 1 | 16 | 80%
Phase 2 | 22 | 2027-02-10 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Kanpur | Kanpur Dehat | Central UP | Tier 3 | New | 16 | 2 | 2 | 0 | 14 | 87.5%
Phase 2 | 23 | 2027-02-12 | Friday | 4 PM - 8 PM | Rath A |  | Host | Azamgarh | Ballia | Eastern UP | Tier 3 | New | 18 | 4 | 4 | 0 | 14 | 77.78%
Phase 2 | 24 | 2027-02-12 | Friday | 4 PM - 8 PM | Rath B |  | Host | Kanpur | Etawah | Central UP | Tier 3 | New | 16 | 10 | 10 | 0 | 6 | 37.5%
Phase 2 | 25 | 2027-02-17 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Vindhyachal | Sonbhadra | Eastern UP | Tier 3 | New | 20 | 2 | 2 | 0 | 18 | 90%
Phase 2 | 26 | 2027-02-17 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Agra | Mainpuri | Western UP | Tier 3 | New | 16 | 3 | 3 | 0 | 13 | 81.25%
Phase 2 | 27 | 2027-02-19 | Friday | 4 PM - 8 PM | Rath A |  | Host | Devipatan | Bahraich | Eastern UP | Tier 3 | Follow-up | 18 | 2 | 2 | 0 | 16 | 88.89% | 1 | 0 | 0 | 0 | 0 | 0
Phase 2 | 28 | 2027-02-19 | Friday | 4 PM - 8 PM | Rath B |  | Host | Agra | Firozabad | Western UP | Tier 3 | New | 18 | 6 | 4 | 2 | 12 | 66.67%
Phase 2 | 29 | 2027-02-24 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Basti | Siddharth Nagar | Eastern UP | Tier 3 | New | 16 | 2 | 2 | 0 | 14 | 87.5%
Phase 2 | 30 | 2027-02-26 | Friday | 4 PM - 8 PM | Rath A |  | Host | Prayagraj | Fatehpur | Eastern UP | Tier 3 | New | 15 | 0 | 0 | 0 | 15 | 100%
Phase 2 | 31 | 2027-02-26 | Friday | 4 PM - 8 PM | Rath B |  | Host | Meerut | Ghaziabad | Western UP | Tier 2 | New | 86 | 141 | 67 | 74 | -55 | -63.95%
Phase 2 | 32 | 2027-03-03 | Wednesday | 4 PM - 8 PM | Rath A |  | Host | Lucknow | Unnao | Central UP | Tier 3 | New | 21 | 4 | 3 | 1 | 17 | 80.95%
Phase 2 | 33 | 2027-03-03 | Wednesday | 4 PM - 8 PM | Rath B |  | Host | Meerut | Gautam Buddha Nagar | Western UP | Tier 3 | New | 77 | 146 | 47 | 99 | -69 | -89.61%
Phase 3 | 1 | 2027-03-05 | Friday | 4 PM - 8 PM | Cluster Yatra | Hathras Cluster | Host | Aligarh | Hathras | Western UP | Tier 3 | New | 13 | 3 | 2 | 1 | 10 | 76.92%
Phase 3 | 1 | 2027-03-05 | Friday | 4 PM - 8 PM | Cluster Yatra | Hathras Cluster | Cluster district | Aligarh | Etah | Western UP | Tier 3 | New | 8 | 0 | 0 | 0 | 8 | 100%
Phase 3 | 1 | 2027-03-05 | Friday | 4 PM - 8 PM | Cluster Yatra | Hathras Cluster | Cluster district | Aligarh | Kasganj | Western UP | Tier 3 | New | 3 | 0 | 0 | 0 | 3 | 100%
Phase 3 | 2 | 2027-03-05 | Friday | 4 PM - 8 PM | Cluster Yatra | Pratapgarh Cluster | Host | Prayagraj | Pratapgarh | Eastern UP | Tier 3 | Follow-up | 9 | 1 | 1 | 0 | 8 | 88.89% | 1 | 20 | 0 | 0 | 0 | 0
Phase 3 | 2 | 2027-03-05 | Friday | 4 PM - 8 PM | Cluster Yatra | Pratapgarh Cluster | Cluster district | Lucknow | Rae Bareli | Central UP | Tier 3 | New | 13 | 5 | 5 | 0 | 8 | 61.54%
Phase 3 | 2 | 2027-03-05 | Friday | 4 PM - 8 PM | Cluster Yatra | Pratapgarh Cluster | Cluster district | Prayagraj | Kaushambi | Eastern UP | Tier 3 | New | 10 | 2 | 2 | 0 | 8 | 80%
Phase 3 | 3 | 2027-03-12 | Friday | 4 PM - 8 PM | Cluster Yatra | Farrukhabad Cluster | Host | Kanpur | Farrukhabad | Central UP | Tier 3 | New | 14 | 2 | 2 | 0 | 12 | 85.71%
Phase 3 | 3 | 2027-03-12 | Friday | 4 PM - 8 PM | Cluster Yatra | Farrukhabad Cluster | Cluster district | Kanpur | Kannauj | Central UP | Tier 3 | New | 11 | 2 | 2 | 0 | 9 | 81.82%
Phase 3 | 3 | 2027-03-12 | Friday | 4 PM - 8 PM | Cluster Yatra | Farrukhabad Cluster | Cluster district | Kanpur | Auraiya | Central UP | Tier 3 | New | 4 | 1 | 1 | 0 | 3 | 75%
Phase 3 | 4 | 2027-03-12 | Friday | 4 PM - 8 PM | Cluster Yatra | Balrampur Cluster | Host | Devipatan | Balrampur | Eastern UP | Tier 3 | New | 10 | 0 | 0 | 0 | 10 | 100%
Phase 3 | 4 | 2027-03-12 | Friday | 4 PM - 8 PM | Cluster Yatra | Balrampur Cluster | Cluster district | Devipatan | Shravasti | Eastern UP | Tier 3 | New | 5 | 0 | 0 | 0 | 5 | 100%
Phase 3 | 5 | 2027-03-17 | Wednesday | 4 PM - 8 PM | Cluster Yatra | Budaun Cluster | Host | Bareilly | Budaun | Western UP | Tier 3 | New | 14 | 1 | 1 | 0 | 13 | 92.86%
Phase 3 | 5 | 2027-03-17 | Wednesday | 4 PM - 8 PM | Cluster Yatra | Budaun Cluster | Cluster district | Moradabad | Sambhal | Western UP | Tier 3 | New | 11 | 1 | 1 | 0 | 10 | 90.91%
Phase 3 | 6 | 2027-03-19 | Friday | 4 PM - 8 PM | Cluster Yatra | Orai (Jalaun) Cluster | Host | Jhansi | Jalaun | Bundelkhand (South UP) | Tier 3 | New | 11 | 3 | 3 | 0 | 8 | 72.73%
Phase 3 | 6 | 2027-03-19 | Friday | 4 PM - 8 PM | Cluster Yatra | Orai (Jalaun) Cluster | Cluster district | Jhansi | Lalitpur | Bundelkhand (South UP) | Tier 3 | New | 6 | 0 | 0 | 0 | 6 | 100%
Phase 3 | 7 | 2027-03-24 | Wednesday | 4 PM - 8 PM | Cluster Yatra | Banda Cluster | Host | Chitrakoot | Banda | Bundelkhand (South UP) | Tier 3 | New | 3 | 0 | 0 | 0 | 3 | 100%
Phase 3 | 7 | 2027-03-24 | Wednesday | 4 PM - 8 PM | Cluster Yatra | Banda Cluster | Cluster district | Chitrakoot | Chitrakoot | Bundelkhand (South UP) | Tier 3 | New | 2 | 0 | 0 | 0 | 2 | 100%
Phase 3 | 7 | 2027-03-24 | Wednesday | 4 PM - 8 PM | Cluster Yatra | Banda Cluster | Cluster district | Chitrakoot | Mahoba | Bundelkhand (South UP) | Tier 3 | New | 1 | 0 | 0 | 0 | 1 | 100%
Phase 3 | 7 | 2027-03-24 | Wednesday | 4 PM - 8 PM | Cluster Yatra | Banda Cluster | Cluster district | Chitrakoot | Hamirpur | Bundelkhand (South UP) | Tier 3 | New | 3 | 1 | 1 | 0 | 2 | 66.67%

## Phase 1 (Oct-Nov 2026)
Yatra # | Event Date | Day | Time | Rath | Mandal | District | Zone | Tier | Visit Type | PM-JAY Universe | NABH Total | Certified | Accredited | Potential Gap | % Potential | Yatras Conducted | Attended | Won | Application in Progress | Hot | Warm
TOTAL | [5 empty] | 23 districts |  |  |  | 1854 | 588 | 450 | 138 | 1266 | 68.28% | 8 | 191 | 6 | 17 | 46 | 5
1 | 2026-10-09 | Friday | 4 PM - 8 PM | Launch (Rath A + B) | Gorakhpur | Gorakhpur | Eastern UP | Tier 3 | Follow-up | 211 | 68 | 58 | 10 | 143 | 67.77% | 3 | 74 | 6 | 1 | 24 | 3
2 | 2026-10-14 | Wednesday | 4 PM - 8 PM | Rath A | Bareilly | Bareilly | Western UP | Tier 3 | New | 211 | 90 | 57 | 33 | 121 | 57.35%
3 | 2026-10-14 | Wednesday | 4 PM - 8 PM | Rath B | Gorakhpur | Kushi Nagar | Eastern UP | Tier 3 | New | 47 | 3 | 3 | 0 | 44 | 93.62%
4 | 2026-10-16 | Friday | 4 PM - 8 PM | Rath A | Moradabad | Moradabad | Western UP | Tier 3 | New | 103 | 40 | 26 | 14 | 63 | 61.17%
5 | 2026-10-16 | Friday | 4 PM - 8 PM | Rath B | Gorakhpur | Maharajganj | Eastern UP | Tier 3 | New | 24 | 1 | 1 | 0 | 23 | 95.83%
6 | 2026-10-23 | Friday | 4 PM - 8 PM | Rath A | Moradabad | Bijnor | Western UP | Tier 3 | New | 91 | 21 | 21 | 0 | 70 | 76.92%
7 | 2026-10-23 | Friday | 4 PM - 8 PM | Rath B | Basti | Sant Kabir Nagar | Eastern UP | Tier 3 | New | 46 | 7 | 7 | 0 | 39 | 84.78%
8 | 2026-10-28 | Wednesday | 4 PM - 8 PM | Rath A | Saharanpur | Muzaffarnagar | Western UP | Tier 3 | New | 44 | 21 | 19 | 2 | 23 | 52.27%
9 | 2026-10-28 | Wednesday | 4 PM - 8 PM | Rath B | Basti | Basti | Eastern UP | Tier 3 | New | 78 | 11 | 10 | 1 | 67 | 85.9%
10 | 2026-10-30 | Friday | 4 PM - 8 PM | Rath A | Saharanpur | Saharanpur | Western UP | Tier 3 | Follow-up | 80 | 34 | 32 | 2 | 46 | 57.5% | 2 | 19 | 0 | 0 | 1 | 2
11 | 2026-10-30 | Friday | 4 PM - 8 PM | Rath B | Ayodhya | Barabanki | Eastern UP | Tier 3 | New | 42 | 4 | 3 | 1 | 38 | 90.48%
12 | 2026-11-04 | Wednesday | 4 PM - 8 PM | Rath A | Saharanpur | Shamli | Western UP | Tier 3 | New | 39 | 9 | 8 | 1 | 30 | 76.92%
13 | 2026-11-04 | Wednesday | 4 PM - 8 PM | Rath B | Lucknow | Lakhimpur Kheri | Central UP | Tier 3 | New | 21 | 1 | 1 | 0 | 20 | 95.24%
14 | 2026-11-13 | Friday | 4 PM - 8 PM | Rath A | Meerut | Bulandshahar | Western UP | Tier 3 | New | 100 | 49 | 41 | 8 | 51 | 51%
15 | 2026-11-13 | Friday | 4 PM - 8 PM | Rath B | Prayagraj | Prayagraj | Eastern UP | Tier 3 | Follow-up | 179 | 45 | 23 | 22 | 134 | 74.86% | 1 | 30 | 0 | 8 | 7 | 0
16 | 2026-11-18 | Wednesday | 4 PM - 8 PM | Rath A | Meerut | Hapur | Western UP | Tier 3 | New | 37 | 6 | 5 | 1 | 31 | 83.78%
17 | 2026-11-18 | Wednesday | 4 PM - 8 PM | Rath B | Vindhyachal | Mirzapur | Eastern UP | Tier 3 | Follow-up | 33 | 8 | 5 | 3 | 25 | 75.76% | 1 | 27 | 0 | 0 | 0 | 0
18 | 2026-11-20 | Friday | 4 PM - 8 PM | Rath A | Aligarh | Aligarh | Western UP | Tier 3 | New | 70 | 29 | 24 | 5 | 41 | 58.57%
19 | 2026-11-20 | Friday | 4 PM - 8 PM | Rath B | Vindhyachal | Bhadohi | Eastern UP | Tier 3 | New | 35 | 4 | 4 | 0 | 31 | 88.57%
20 | 2026-11-25 | Wednesday | 4 PM - 8 PM | Rath A | Kanpur | Kanpur Nagar | Central UP | Tier 2 | New | 194 | 90 | 60 | 30 | 104 | 53.61%
21 | 2026-11-25 | Wednesday | 4 PM - 8 PM | Rath B | Varanasi | Chandauli | Eastern UP | Tier 3 | New | 62 | 9 | 9 | 0 | 53 | 85.48%
22 | 2026-11-27 | Friday | 4 PM - 8 PM | Rath A | Jhansi | Jhansi | Bundelkhand (South UP) | Tier 3 | Follow-up | 71 | 34 | 31 | 3 | 37 | 52.11% | 1 | 41 | 0 | 8 | 14 | 0
23 | 2026-11-27 | Friday | 4 PM - 8 PM | Rath B | Azamgarh | Mau | Eastern UP | Tier 3 | New | 36 | 4 | 2 | 2 | 32 | 88.89%
Source: UP GY district schedule finalised 15 Sep 2026; hospital figures from 'Updated District List data.xlsx' -> (VF) Final Sheet. 23 workshops, 12 event days, two Raths in parallel on every date after the 09 Oct Gorakhpur launch. All sessions: Entry Level Certification, 4 PM - 8 PM.

## Phase 2 (Jan-Mar 2027)
Yatra # | Event Date | Day | Time | Rath | Mandal | District | Zone | Tier | Visit Type | PM-JAY Universe | NABH Total | Certified | Accredited | Potential Gap | % Potential | Yatras Conducted | Attended | Won | Application in Progress | Hot | Warm
TOTAL | [5 empty] | 33 districts |  |  |  | 1645 | 794 | 484 | 310 | 851 | 51.73% | 16 | 298 | 16 | 5 | 25 | 20
1 | 2027-01-06 | Wednesday | 4 PM - 8 PM | Rath A | Varanasi | Jaunpur | Eastern UP | Tier 3 | Follow-up | 58 | 9 | 9 | 0 | 49 | 84.48% | 1 | 22 | 2 | 1 | 3 | 2
2 | 2027-01-06 | Wednesday | 4 PM - 8 PM | Rath B | Meerut | Meerut | Western UP | Tier 3 | Follow-up | 129 | 67 | 40 | 27 | 62 | 48.06% | 1 | 30 | 0 | 0 | 0 | 0
3 | 2027-01-08 | Friday | 4 PM - 8 PM | Rath A | Gorakhpur | Deoria | Eastern UP | Tier 3 | Follow-up | 32 | 5 | 5 | 0 | 27 | 84.38% | 1 | 29 | 3 | 0 | 3 | 1
4 | 2027-01-08 | Friday | 4 PM - 8 PM | Rath B | Agra | Agra | Western UP | Tier 2 | Follow-up | 89 | 56 | 45 | 11 | 33 | 37.08% | 2 | 14 | 3 | 0 | 2 | 3
5 | 2027-01-13 | Wednesday | 4 PM - 8 PM | Rath A | Ayodhya | Ambedkar Nagar | Eastern UP | Tier 3 | Follow-up | 30 | 3 | 3 | 0 | 27 | 90% | 1 | 32 | 4 | 2 | 1 | 3
6 | 2027-01-13 | Wednesday | 4 PM - 8 PM | Rath B | Agra | Mathura | Western UP | Tier 3 | Follow-up | 70 | 25 | 21 | 4 | 45 | 64.29% | 2 | 42 | 0 | 0 | 0 | 0
7 | 2027-01-15 | Friday | 4 PM - 8 PM | Rath A | Ayodhya | Ayodhya | Eastern UP | Tier 3 | Follow-up | 30 | 7 | 6 | 1 | 23 | 76.67% | 1 | 32 | 2 | 1 | 2 | 1
8 | 2027-01-15 | Friday | 4 PM - 8 PM | Rath B | Bareilly | Pilibhit | Western UP | Tier 3 | Follow-up | 27 | 4 | 3 | 1 | 23 | 85.19% | 1 | 25 | 0 | 0 | 0 | 0
9 | 2027-01-20 | Wednesday | 4 PM - 8 PM | Rath A | Ayodhya | Sultanpur | Eastern UP | Tier 3 | Follow-up | 37 | 7 | 7 | 0 | 30 | 81.08% | 1 | 35 | 1 | 1 | 1 | 6
10 | 2027-01-20 | Wednesday | 4 PM - 8 PM | Rath B | Bareilly | Shahjahanpur | Western UP | Tier 3 | New | 32 | 11 | 10 | 1 | 21 | 65.62%
11 | 2027-01-22 | Friday | 4 PM - 8 PM | Rath A | Ayodhya | Amethi | Eastern UP | Tier 3 | New | 24 | 3 | 3 | 0 | 21 | 87.5%
12 | 2027-01-22 | Friday | 4 PM - 8 PM | Rath B | Moradabad | Rampur | Western UP | Tier 3 | New | 23 | 5 | 4 | 1 | 18 | 78.26%
13 | 2027-01-27 | Wednesday | 4 PM - 8 PM | Rath A | Devipatan | Gonda | Eastern UP | Tier 3 | Follow-up | 29 | 4 | 4 | 0 | 25 | 86.21% | 1 | 0 | 1 | 0 | 0 | 0
14 | 2027-01-27 | Wednesday | 4 PM - 8 PM | Rath B | Moradabad | Amroha | Western UP | Tier 3 | New | 23 | 7 | 4 | 3 | 16 | 69.57%
15 | 2027-01-29 | Friday | 4 PM - 8 PM | Rath A | Varanasi | Varanasi | Eastern UP | Tier 3 | Follow-up | 231 | 90 | 57 | 33 | 141 | 61.04% | 1 | 6 | 0 | 0 | 2 | 0
16 | 2027-01-29 | Friday | 4 PM - 8 PM | Rath B | Meerut | Baghpat | Western UP | Tier 3 | New | 24 | 8 | 7 | 1 | 16 | 66.67%
17 | 2027-02-03 | Wednesday | 4 PM - 8 PM | Rath A | Lucknow | Lucknow | Central UP | Tier 2 | Follow-up | 326 | 137 | 90 | 47 | 189 | 57.98% | 1 | 20 | 0 | 0 | 11 | 2
18 | 2027-02-03 | Wednesday | 4 PM - 8 PM | Rath B | Lucknow | Hardoi | Central UP | Tier 3 | New | 19 | 1 | 1 | 0 | 18 | 94.74%
19 | 2027-02-05 | Friday | 4 PM - 8 PM | Rath A | Azamgarh | Azamgarh | Eastern UP | Tier 3 | Follow-up | 36 | 16 | 14 | 2 | 20 | 55.56% | 1 | 11 | 0 | 0 | 0 | 2
20 | 2027-02-05 | Friday | 4 PM - 8 PM | Rath B | Lucknow | Sitapur | Central UP | Tier 3 | New | 19 | 3 | 2 | 1 | 16 | 84.21%
21 | 2027-02-10 | Wednesday | 4 PM - 8 PM | Rath A | Varanasi | Ghazipur | Eastern UP | Tier 3 | New | 20 | 4 | 3 | 1 | 16 | 80%
22 | 2027-02-10 | Wednesday | 4 PM - 8 PM | Rath B | Kanpur | Kanpur Dehat | Central UP | Tier 3 | New | 16 | 2 | 2 | 0 | 14 | 87.5%
23 | 2027-02-12 | Friday | 4 PM - 8 PM | Rath A | Azamgarh | Ballia | Eastern UP | Tier 3 | New | 18 | 4 | 4 | 0 | 14 | 77.78%
24 | 2027-02-12 | Friday | 4 PM - 8 PM | Rath B | Kanpur | Etawah | Central UP | Tier 3 | New | 16 | 10 | 10 | 0 | 6 | 37.5%
25 | 2027-02-17 | Wednesday | 4 PM - 8 PM | Rath A | Vindhyachal | Sonbhadra | Eastern UP | Tier 3 | New | 20 | 2 | 2 | 0 | 18 | 90%
26 | 2027-02-17 | Wednesday | 4 PM - 8 PM | Rath B | Agra | Mainpuri | Western UP | Tier 3 | New | 16 | 3 | 3 | 0 | 13 | 81.25%
27 | 2027-02-19 | Friday | 4 PM - 8 PM | Rath A | Devipatan | Bahraich | Eastern UP | Tier 3 | Follow-up | 18 | 2 | 2 | 0 | 16 | 88.89% | 1 | 0 | 0 | 0 | 0 | 0
28 | 2027-02-19 | Friday | 4 PM - 8 PM | Rath B | Agra | Firozabad | Western UP | Tier 3 | New | 18 | 6 | 4 | 2 | 12 | 66.67%
29 | 2027-02-24 | Wednesday | 4 PM - 8 PM | Rath A | Basti | Siddharth Nagar | Eastern UP | Tier 3 | New | 16 | 2 | 2 | 0 | 14 | 87.5%
30 | 2027-02-26 | Friday | 4 PM - 8 PM | Rath A | Prayagraj | Fatehpur | Eastern UP | Tier 3 | New | 15 | 0 | 0 | 0 | 15 | 100%
31 | 2027-02-26 | Friday | 4 PM - 8 PM | Rath B | Meerut | Ghaziabad | Western UP | Tier 2 | New | 86 | 141 | 67 | 74 | -55 | -63.95%
32 | 2027-03-03 | Wednesday | 4 PM - 8 PM | Rath A | Lucknow | Unnao | Central UP | Tier 3 | New | 21 | 4 | 3 | 1 | 17 | 80.95%
33 | 2027-03-03 | Wednesday | 4 PM - 8 PM | Rath B | Meerut | Gautam Buddha Nagar | Western UP | Tier 3 | New | 77 | 146 | 47 | 99 | -69 | -89.61%
Source: UP GY Phase 2 plan. Selection: 70% potential on the absolute NABH gap (PM-JAY Universe - NABH Total) + 30% leads (Hot + Application in Progress). Districts with PM-JAY universe under 15 held for Phase 3. Ghaziabad and Gautam Buddha Nagar placed last (negative gap). Rath A/B assigned by order within each date.

## Phase 3 Clusters (Mar 2027)
Yatra # | Event Date | Day | Time | Cluster | Role | Mandal | District | Zone | Tier | Visit Type | PM-JAY Universe | NABH Total | Certified | Accredited | Potential Gap | % Potential | Yatras Conducted | Attended | Won | Application in Progress | Hot | Warm
TOTAL | [6 empty] | 19 districts |  |  |  | 151 | 22 | 21 | 1 | 129 | 85.43% | 1 | 20 | 0 | 0 | 0 | 0
1 | 2027-03-05 | Friday | 4 PM - 8 PM | Hathras Cluster | Host | Aligarh | Hathras | Western UP | Tier 3 | New | 13 | 3 | 2 | 1 | 10 | 76.92%
1 | 2027-03-05 | Friday | 4 PM - 8 PM | Hathras Cluster | Cluster district | Aligarh | Etah | Western UP | Tier 3 | New | 8 | 0 | 0 | 0 | 8 | 100%
1 | 2027-03-05 | Friday | 4 PM - 8 PM | Hathras Cluster | Cluster district | Aligarh | Kasganj | Western UP | Tier 3 | New | 3 | 0 | 0 | 0 | 3 | 100%
2 | 2027-03-05 | Friday | 4 PM - 8 PM | Pratapgarh Cluster | Host | Prayagraj | Pratapgarh | Eastern UP | Tier 3 | Follow-up | 9 | 1 | 1 | 0 | 8 | 88.89% | 1 | 20 | 0 | 0 | 0 | 0
2 | 2027-03-05 | Friday | 4 PM - 8 PM | Pratapgarh Cluster | Cluster district | Lucknow | Rae Bareli | Central UP | Tier 3 | New | 13 | 5 | 5 | 0 | 8 | 61.54%
2 | 2027-03-05 | Friday | 4 PM - 8 PM | Pratapgarh Cluster | Cluster district | Prayagraj | Kaushambi | Eastern UP | Tier 3 | New | 10 | 2 | 2 | 0 | 8 | 80%
3 | 2027-03-12 | Friday | 4 PM - 8 PM | Farrukhabad Cluster | Host | Kanpur | Farrukhabad | Central UP | Tier 3 | New | 14 | 2 | 2 | 0 | 12 | 85.71%
3 | 2027-03-12 | Friday | 4 PM - 8 PM | Farrukhabad Cluster | Cluster district | Kanpur | Kannauj | Central UP | Tier 3 | New | 11 | 2 | 2 | 0 | 9 | 81.82%
3 | 2027-03-12 | Friday | 4 PM - 8 PM | Farrukhabad Cluster | Cluster district | Kanpur | Auraiya | Central UP | Tier 3 | New | 4 | 1 | 1 | 0 | 3 | 75%
4 | 2027-03-12 | Friday | 4 PM - 8 PM | Balrampur Cluster | Host | Devipatan | Balrampur | Eastern UP | Tier 3 | New | 10 | 0 | 0 | 0 | 10 | 100%
4 | 2027-03-12 | Friday | 4 PM - 8 PM | Balrampur Cluster | Cluster district | Devipatan | Shravasti | Eastern UP | Tier 3 | New | 5 | 0 | 0 | 0 | 5 | 100%
5 | 2027-03-17 | Wednesday | 4 PM - 8 PM | Budaun Cluster | Host | Bareilly | Budaun | Western UP | Tier 3 | New | 14 | 1 | 1 | 0 | 13 | 92.86%
5 | 2027-03-17 | Wednesday | 4 PM - 8 PM | Budaun Cluster | Cluster district | Moradabad | Sambhal | Western UP | Tier 3 | New | 11 | 1 | 1 | 0 | 10 | 90.91%
6 | 2027-03-19 | Friday | 4 PM - 8 PM | Orai (Jalaun) Cluster | Host | Jhansi | Jalaun | Bundelkhand (South UP) | Tier 3 | New | 11 | 3 | 3 | 0 | 8 | 72.73%
6 | 2027-03-19 | Friday | 4 PM - 8 PM | Orai (Jalaun) Cluster | Cluster district | Jhansi | Lalitpur | Bundelkhand (South UP) | Tier 3 | New | 6 | 0 | 0 | 0 | 6 | 100%
7 | 2027-03-24 | Wednesday | 4 PM - 8 PM | Banda Cluster | Host | Chitrakoot | Banda | Bundelkhand (South UP) | Tier 3 | New | 3 | 0 | 0 | 0 | 3 | 100%
7 | 2027-03-24 | Wednesday | 4 PM - 8 PM | Banda Cluster | Cluster district | Chitrakoot | Chitrakoot | Bundelkhand (South UP) | Tier 3 | New | 2 | 0 | 0 | 0 | 2 | 100%
7 | 2027-03-24 | Wednesday | 4 PM - 8 PM | Banda Cluster | Cluster district | Chitrakoot | Mahoba | Bundelkhand (South UP) | Tier 3 | New | 1 | 0 | 0 | 0 | 1 | 100%
7 | 2027-03-24 | Wednesday | 4 PM - 8 PM | Banda Cluster | Cluster district | Chitrakoot | Hamirpur | Bundelkhand (South UP) | Tier 3 | New | 3 | 1 | 1 | 0 | 2 | 66.67%
Source: UP GY Phase 3 plan. 19 low-universe districts (PM-JAY universe under 15) grouped into 7 cluster yatras, each hosted at the first district named. 31 Mar 2027 held as reserve date / state-level Gunvatta Manthan and certification ceremony.

## Summary
Phase | Window | Yatras | Districts | PM-JAY Universe | NABH Total | Potential Gap | % Potential | Hot Leads | Application in Progress | Warm Leads
TOTAL (all phases) | 09 Oct 2026 - 24 Mar 2027 | 63 | 75 | 3650 | 1404 | 2246 | 61.53% | 71 | 22 | 25
Phase 1 | 09 Oct - 27 Nov 2026 | 23 | 23 | 1854 | 588 | 1266 | 68.28% | 46 | 17 | 5
Phase 2 | 06 Jan - 03 Mar 2027 | 33 | 33 | 1645 | 794 | 851 | 51.73% | 25 | 5 | 20
Phase 3 | 05 Mar - 24 Mar 2027 | 7 | 19 | 151 | 22 | 129 | 85.43% | 0 | 0 | 0
Notes
All sessions: NABH Entry Level Certification workshop, 4 PM - 8 PM.
Hospital and lead figures are from 'Updated District List data.xlsx' -> sheet '(VF) Final Sheet' (75 districts).
Potential Gap = PM-JAY Universe - NABH Total. Gautam Buddha Nagar (-69) and Ghaziabad (-55) have a negative gap.
Lead stages: Won = already NABH certified/accredited; Application in Progress; Hot = will take NABH within 6 months; Warm = 6-12 months.
Visit Type: 'Follow-up' = a yatra has already been conducted in that district; 'New' = first visit.
Phase 1 + Phase 2 + Phase 3 = 75 districts, no district counted twice. 63 yatras in total.
State universe: 3,650 PM-JAY empanelled hospitals; NABH 1,404 (955 certified + 449 accredited); potential gap 2,246.